## Sheet1
Task name | Duration | Start Date | Finish Date | % complete | Assigned To
Install dev tools | 2 Days | 2011-12-07 | 2011-12-07 | 100% | SC, EH, TP, RT
Learn ruby essentials | 5 Days | 2011-12-07 | 2012-01-07 | 100% | SC, EH, TP, RT
Create domain model (DM) | 9 | 2011-12-07 | 2011-12-16 | 100% | SC, TP, EH
Assess and compile risks into table |  | 2011-12-07 | 2011-12-16 | 100% | TP
Make who-done-what table | 1 Day | 2011-12-07 | 2011-12-16 | 100% | RT
Make plan table rough draft | 1 Day | 2011-12-07 | 2011-12-09 | 100% | TP
Compile M2 documents |  | 2011-12-07 | 2011-12-16 | 100% | EH
Show client DM |  | 2011-12-07 | 2011-12-16 | 100% | SC, EH, TP, RT
Make System Sequence Diagram (SSD) |  | 2012-01-07 | 2012-01-08 |  | SC, EH, TP, RT
Make Operation Contract (OC) |  | 2012-01-07 | 2012-01-08 |  | SC, EH, TP, RT
Develop design model |  | 2012-01-07 | 2012-01-08 |  | SC, EH, TP, RT
Familiarize with Sinatra and HAML |  | 2012-01-09 | 2012-02-17 |  | SC, EH, TP, RT
Basic code structure |  | 2012-01-09 | 2012-01-12 |  | SC, EH, TP, RT
Code GUI framework |  | 2012-01-09 | 2012-01-13 |  | TP, RT
Code database framework |  | 2012-01-09 | 2012-01-13 |  | SC, EH
Show client framework |  | 2012-01-11 | 2012-01-13 |  | SC, EH, TP, RT
Compile M3 documents |  | 2012-01-11 | 2012-01-13 |  | EH, RT
Update M3 documents |  |  | 2012-01-28 |  | -
Code domain layer items |  |  | 2012-01-28 |  | -
Compile M4 documents |  |  | 2012-01-28 |  | -
Update documents: DM, SSD, etc. |  |  | 2012-01-28 |  | -
Finish up coding |  |  | 2012-02-17 |  | -
System tests |  |  | 2012-02-17 |  | -
Write up GoF features |  |  | 2012-02-17 |  | -
Compile M5 documents |  |  | 2012-02-17 |  | -

## Sheet2
ID | Risk | Probability | Impact | Strategy | Outcome | Resources
R1 | Difficulty learning a new language and platform | Medium | Slow and buggy code development | Complete dev preparations together and do language tutorials | High quality code, minimal schedule delay. | Time
R2 | Difficulty configuring server-side of application. | Medium | impedes code testing, results in delays | Work closely with network expert to configure server | quick and painless server configuration. | Time, Tim
R3 | Extraneous CSSE374 induced difficulty (ie adding unneeded patterns for practice) slowing project | Medium | impedes progress, results in delays | Do work in a timely manner, building extra time into the schedule to fix mistakes. | enough development time allows complexity-based bugs to be removed. | Time
R4 | Producing an inacurate model during the design phase. | Medium | negativly impact quality of final product. | regular iteration and regular communication with client | design problems are made apparent through iterations | Time, Tim

## Sheet3
Iteration | Completed
basic GUI
database created with sinatra
basic search capability
item addition
item viewing
item modification
advanced search options
polished GUI